## Sheet1
Defect ID | Category Name | Title | Summary | Steps to Reproduce | Test Data | Expected Results | Actual Results | Enviroment | Related_To | Reported By | Priority | Severity | Status | Attach | Comments of dev team | Comments of testing team
NOP_001 | Products Page | All products display the same incorrect photo | When user login to the website, Products page will open and user will see that all products or items have the same photo | 1- Open the website 2- Enter valid data 3- login 4- Check products photos | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -Products page will open and products will appear with different photos | - All products appear with the same photo | Google chrome | TC_001 | Me | High | High | Closed
NOP_002 | Products Page | Incorrect product titles "Sauce Labs" Repeated in all titles | When user login to the website, Products page will open and all products will appear with the incorrect titles | 1- Open the website 2- Enter valid data 3- login 4- Go to any product 5- Check product titles | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -The product titles should accurately reflect the product names without contain "Sauce Labs." | - All product titles include the extra text "Sauce Labs" repeated | Google chrome |  | Me | High | Low | Reopen
NOP_003 | Products Page | Incorrect product redirection | When user login to the website, products page will open and when user click on any specific item, website will redirect them to antother product with different photos and titles | 1- Open the website 2- Enter valid data 3- login 4- Click on any product | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -User can select specific item and click on it to redirect the user to the corresponding product page | -After selecting a product, the user is redirected to a different item's page. | Google chrome |  | Me | High | High | Closed
NOP_004 | Products Page | "Add to cart" input is not working properly with some products | - When user login to the website, products page will open and products will appear, user can't "add to cart" desired items | 1- Open the website with google chrome browser 2- Enter valid data 3- login 4- Click select product 5- Click on "Add to cart" | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - User can "Add to cart" any desired products | -"Add to cart" input is not working properly with all products | Google chrome |  | Me | High | High | Closed |  |  | -Please note that this error occurs specifically when using Google Chrome and does not appear when accessing the site with Firefox.
NOP_005 | Home page | User can't click on "remove" input after adding selected item to the cart in the home page on google chrome browser | -When user open the page products, and selsect specific item and add it to the cart, "Remove" button will appear beside the selected item when user click on it to remove the item, the input is not working, user has to leave the products page and go to the cart to remove the selected item. | 1- Open the website 2- Enter valid data 3- login 4- "Add to cart" any specific item 5- Try click on "remove" appear after clicking on "add to cart" | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -User can "Add to cart" and "remove" items while shopping without being obligated to go to the cart | -User can't remove the selected item while shopping, user has to go to the cart to remove it | Google chrome |  | Me | Medium | Low | Closed |  |  | -Please note that this error occurs specifically when using Google Chrome and does not appear when accessing the site with Firefox.
NOP_006 | Products Page | Users can't access additional product pages as there is no other product pages | -When user open the products page only 6 products will appear and there is no other pages to reload and also when user scroll the site product page no other results reload | 1- Open the website 2- Enter valid data 3- login 4- scroll the page products and check other products pages | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -Users should be able to navigate to additional product pages to view more products. | -User can't navigate additional products page | Google chrome |  | Me | High | High | Reopen
NOP_007 | Home page | - "Sauce Labs Backpack" title contains incorrect data structure "carry.allTheThings()" | - When user open the website, products page will show up with product title "Sauce Labs Backpack" that contains incorrect data structure "carry.allTheThings()" | 1- Open the website 2- Enter valid data 3- login 4- Check the data product titled with "Sauce Labs Backpack" | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -Products page shoiuld appear with correct data structure | -The product title "Sauce Labs Backpack" contains incorrect data structure "carry.allTheThings()" | Google chrome |  | Me | Low | Low | Reopen
NOP_008 | Home Page | - Search Button dosen't exsist on the website | - When user open the websit and wants to search for specific item, user will not find search button | 1- Open the website 2- Enter valid data 3- login 4- check the "search" button existence | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - User can search on any product | -User can't find search button to search for specific items | Google chrome |  | Me | High | High | Reopen
NOP_009 | Home Page | - Incorrect Product Title "Test.allTheThings() T-Shirt (Red)" | - When user open the website, product pages will show up, there is an incorrect product title "Test.allTheThings() T-Shirt (Red)" will appear to the user | 1- Open the website 2- Enter valid data 3- login 4- scroll the website 5- Search for the product titled "Test.allTheThings() T-Shirt (Red)" | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -The product title should accurately reflect the product without any error | - The product titled "Test.allTheThings() T-Shirt (Red)" contains incorrect title | Google chrome |  | Me | Medium | Low | Reopen
NOP_010 | Products Page | -Fitration input is not working properly | - When user open the website, Products pages will appear and user can't use filter input as it is not working properly | 1- Open the website 2- Enter valid data 3- login 4- Check the filteration input | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - User can use filtration input to filter products | - User can't use filter input as it is not working properly | Google chrome |  | Me | High | High | Closed
NOP_011 | Products Page | -When User select product "Sauce Labs Fleece Jacket" another page open with "Item not found" | -When user selects the "Sauce Labs Fleece Jacket" item, which is the second item on the right, another page opens indicating that the item is not found. | 1- Open the website 2- Enter valid data 3- login 4- Click on "Sauce Labs Fleece Jacket" product 5- Check the product title with "item not found" | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - User can open the mentioned product properly and see the same selected product details | - User can't see the corresponding details of the "Sauce Labs Fleece Jacket" product as it's not found | Google chrome |  | Me | Low | Low | Closed
NOP_012 | Products Page | -User can't reload additional product pages due to their unavailabilty | -When user open the site and wants to reload additinal product pages, users will find that after browsing the page, no further pages or products are available for viewing | 1- Open the website 2- Enter valid data 3- login 4- Check the availabilty of additional product pages | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -Users have the capability to reload the page and access additional product pages for shopping purposes. | -Users dosen't have the capability to reload the page and access additional product pages for shopping purposes. | Google chrome |  | Me | High | High | Reopen
NOP_013 | Products Page | -Users are unable to view the available product sizes or colors. | -When user open the site and products show up, users are unable to select specific sizes or colors for the desired items. | 1- Open the website 2- Enter valid data 3- login 4- Check the availabilty of items sizes and colors | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -Users have the capability to select specific sizes and colors for the desired items | -Users dosen't have the capability to select specific sizes and colors for the desired items | Google chrome |  | Me | High | High | Reopen
NOP_014 | Products Page | - "Out of Stock" Indicator Not Visible for Products | - When user open the site and products show up, users can't determin if the desired product "out of stock" as the "out of stock" indicator is not displayed. | 1- Open the website 2- Enter valid data 3- login 4- Check the "out of stock" indicator | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - An "out of stock" indicator appears beside the unavailable products | - An "out of stock" indicator doesn't appear beside the unavailable products | Google chrome |  | Me | Medium | Low | Reopen
NOP_015 | Products Page | - Check the absence of product quantity input field. | - When user selects the desired product and wants to purchase more than one piece of the same item, User will not find a quantity input field available to adjust the number of desired pieces. | 1- Open the website 2- Enter valid data 3- login 4- Check the "product quantity" input field | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -User can see product's quantity input field allwoing them to adjust the number of desired products | -User can't see product's quantity input field allowing them to adjust the number of desired products | Google chrome |  | Me | High | Medium | Reopen
NOP_016 | Products Page | - Incorrect product title spelling and describtion "Sauce Labs Onesie" | - User will notice the item title "Sauce Labs Onesie" contains spelling mistake as it should be "Sauce Labs Onesize" and wrong description of the product photo | 1- Open the website 2- Enter valid data 3- login 4- select "Sauce Labs Bolt T-Shirt" product 5- Check title description | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - Product items should be appeared with correct spelling and title description | - Users will notice a spelling error in the item title "Sauce Labs Onesie" and incorrect title description | Google chrome |  | Me | Low | Low | Reopen
NOP_017 | Home page | -Mismatch Between Selected Items Quantity and Cart Basket Count on google chrome browser | - When user add to cart 3 items, the red number displayed in the Cart Basket that appear above on the right will be 4. | 1- Open the website on google chrome browser 2- Enter valid data 3- login 4- Add to cart 3 items 5- Check the Cart Basket that appear above on the right | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - The red number displayed in the cart basket should be matched with the total quantity of selected items | -The red number displayed in the cart basket is not matched with the total quantity of selected items | Google chrome |  | Me | Medium | Low | Closed | https://drive.google.com/file/d/1zdeOe1h6WlLp0FTexRe44UuqSdBs5Xyv/view?usp=drive_link |  | -Please note that this error occurs specifically when using Google Chrome and does not appear when accessing the site with Firefox.
NOP_018 | Home page | -Website crashes when clicking on the cart basket after adding to cart more than 2 items | -When user add to cart more than 2 items and go to the cart to check them, website will crash on google chrome browser | 1- Open the website on google chrome browser 2- Enter valid data 3- login 4- Add to cart 3 items 5- Click on Cart Basket appear above on the right | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - User can be able to add all desired items to the cart and go to the cart to check them without crashing | - User can't be able to add to the cart more than two as the site will crash when user goes to the cart | Google chrome |  | Me | High | High | Closed | https://drive.google.com/file/d/1zVvrmobyKP0qnk4ilgG2EdpJeV0NCaBY/view?usp=drive_link |  | -Please note that this error occurs specifically when using Google Chrome and does not appear when accessing the site with Firefox.
NOP_019 | Products Page | -"Remove" and "Add to cart" buttons malfunction on product details page | -When user select specific product and the product page open, user can't click on remove or add to cart buttons | 1- Open the website 2- Enter valid data 3- login 4- select any product 5- Click on remove or add to cart buttons | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - user can't add to cart or remove products properly from the product page | - user can't add to cart or remove products from the product page | Google chrome |  |  | High | High | Closed
NOP_020 | Products Page | -Incorrect price displayed on "Sauce Labs Fleece Jacket" product page | -When user select "Sauce Labs Fleece Jacket" product page will appear with incorrect price | 1- Open the website 2- Enter valid data 3- login 4- Click on "Sauce Labs Fleece Jacket" product 5- Check the product price | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | - The price displayed should accurately reflect the cost of the "Sauce Labs Fleece Jacket" product. | - The price displayed does not match the correct price of the product. | Google chrome |  |  | Medium | Low | Closed
NOP_021 | Products Page | -Incorrect title description displayed for "Sauce Labs Onesie" product | - when user select "Sauce Labs Onesie" product, incorrect title description appear "Test.allTheThings() T-Shirt (Red)" | 1- Open the website 2- Enter valid data 3- login 4- Click on "Sauce Labs Onesie" product 5- Check the product title | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -The product title should accurately reflect the product without any error | - After selected specific item, incorrect title in product page "Test.allTheThings() T-Shirt (Red)" displayed to the user | Google chrome |  |  | Low | Low | Closed
NOP_022 | Products Page | - Incorrect data displayed for "Sauce Labs Fleece Jacket" | - When user select "Sauce Labs Fleece Jacket" product, incorrect product details or description displayed under the product title | 1- Open the website 2- Enter valid data 3- login 4- Click on "Sauce Labs Onesie" product 5- Check the product details under the title | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -The displayed data should accurately represent the "Sauce Labs Fleece Jacket" product. | - The displayed data is inconsistent with the actual product title "inconsistent with the actual product details" | Google chrome |  |  | Medium | Low | Closed
NOP_023 | Products Page | - "Remove" button displayed on "Sauce Labs Bolt T-Shirt" product page without adding the item to cart | - When user select "Sauce Labs Onesie" product, and the product page will displayed with remove button without adding the mentioned item to the cart | 1- Open the website 2- Enter valid data 3- login 4- Click on "Sauce Labs Bolt T-Shirt" product 5- Check the presence of "Remove" button | - Website URL : https://www.saucedemo.com/ - User name: problem_user - Password: secret_sauce | -The "Remove" button should not be displayed until user add item to the cart | - the product page is displayed with remove button without adding the mentioned item to the cart | Google chrome |  |  | High | Medium | Closed
Please be noted that i can't open the cart on google chrome and firefox browsers because of crashing as i attached photo in "NOP_018" bug so i already wrote bug reports on the catalog page or the home page and the products page.